## Slide 1: Working Out Loud with AI
Building Agile Change Momentum
Templates and Examples

## Slide 2: From Sensemaking to Structured Action: Plan on a Page

## Slide 3
January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  | 
Week of 1/5 | Week of 1/12 | Week of 1/19 | Week of 1/26 | Week of 2/2 | Week of 2/9 | Week of 2/16 | Week of 2/23 | Week of 3/2 | Week of 3/9 | Week of 3/16 | Week of 3/23 | Week of 3/30
Project
Milestones
Comms
Training
Engagement
Measurement
Feedback
Template

## Slide 4: Generate a Plan on a Page
Prompt:
I am creating a high-level, agile Plan on a Page for a change initiative.
Context about the change:
Change description: [brief description of the change or solution]
Type of change: [process, technology, behavior, operating model, etc.]
Organizational context: [size, pace of change, constraints, seasonality, etc.]
Audiences / rollout groups:
Audience 1: [role, size, location, readiness level]
Audience 2: [role, size, location, readiness level]
Audience 3: [role, size, location, readiness level]
Known constraints and anchors:
Target go-live dates by audience:
  Audience 1: [date]
  Audience 2: [date]
  Audience 3: [date]
Any blackout periods, dependencies or risks: [if applicable]
Planning assumptions:
Work in rolling, agile phases
Activities should follow a reasonable sequence relative to each go-live
Dates can be approximate and expressed as “week of”
Please generate:
A Plan on a Page organized by these swim lanes:
  Communications
  Training
  Engagement
  Feedback
  Measurement
For each swim lane, list key activities that typically support a successful rollout for this type of change
Align activities to each audience group and their go-live date
Suggest approximate timing for each activity (e.g., weeks before or after go-live, then convert to “week of” dates)
Include key milestones such as:
  Awareness and invite communications
  Roadshows or briefings
  Training prep and delivery
  Engagement touchpoints (office hours, open sessions)
  Pulse checks and feedback loops
  Usage monitoring and reporting
Output format:
Table format, visual, use my template for what I’m going towards
Columns: Dates
Rows: Swim Lane
Cells: Audience | Activity
Guidance:
Optimize for clarity and flow, not perfection
Call out where human judgment or iteration would likely be needed
Treat this as a first draft meant to be refined with stakeholders
Prompt
© 2025 The Change Curiosity Lab. All rights reserved.

## Slide 5
January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  | 
Week of 1/5 | Week of 1/12 | Week of 1/19 | Week of 1/26 | Week of 2/2 | Week of 2/9 | Week of 2/16 | Week of 2/23 | Week of 3/2 | Week of 3/9 | Week of 3/16 | Week of 3/23 | Week of 3/30
Project
Milestones
Comms
Training
Engagement
Measurement
Feedback
2/27
Group 2 Go Live
1/30
Group 1 Go Live
3/27
Group 3 Go Live
Group 3
Monitor Usage
1/14
Group 1 Roadshow Follow-Up
Group 1
Monitor Usage
Group 1
Usage Report
2/16
Group 1
Pulse Check Survey
2/2
Group 2 Awareness and Roadshow Invite
3/2
Group 3 Awareness and Roadshow Invite
3/9
Group 2
Pulse Check Survey
Group 2
Monitor Usage
Group 2
Usage Report
1/5
Group 1 Awareness and Roadshow Invite
2/11
Group 2 Roadshow Follow-Up
1/14
Open Door Session
1/14
Open Door Session
3/13
Group 3 Roadshow Follow-Up
1/14
Open Door Session
Share Success Stories
Share Success Stories
Group 1
Tailor
1/12
Group 1 Tailored Roadshow + Training + User Guide
Group 2
Tailor
2/9
Group 2 Tailored Roadshow + Training + User Guide
Group 3
Tailor
3/9
Group 3 Tailored Roadshow + Training + User Guide
Develop + Publish FAQ
Update + Republish FAQ
Update + Republish FAQ
Collect Success Stories
Collect Success Stories
Collect Success Stories
Monthly AI Newsletter
Monthly AI Newsletter
Monthly AI Newsletter
1/30
Town Hall
2/27
Town Hall
3/27
Town Hall
Update + Republish FAQ
Iterate solution and change support as pilot feedback is received
Iterate solution and change support as feedback is received
Iterate solution and change support as feedback is received, new teams onboarded
Iterate solution and change support as feedback is received, new teams onboarded
Group 1
Readiness Check / Pre-KPI
Group 2
Readiness Check / Pre-KPI
Group 3
Readiness Check / Pre-KPI
Example

## Slide 6: The AI-Infused Agile Change Canvas

## Slide 7
PROBLEM/OPPORTUNITY (WHAT)
Background to what brought this about, the catalyst. This provides context and background.
This will help you build your story.
VALUE PROPOSITION (WHY)
Why we need to change and one or two benefit statements.
Often this is about disruption, legislative changes, competitor activity, customer expectations.
AI-Infused Change Canvas
Product Owner: <this can be the Project Sponsor> | Audience: <the group/sub-group affected by the change> | Date: <the date you prepare this document>
Change Initiative: <the project name, what’s the change?> | Change Lead: <the person leading the change effort> | Go Live Date: <the date this change will go live>
CHANGE STRATEGIES (HOW)
What are the key change activities for this change and/or audience?
What are the appropriate channels? E.g. email, forums, learning sessions?
KEY MESSAGES/WIIFM
What is changing, what stays the same
What you need to do differently
Consider target audiences for different messages
Key dates, implementation date/s
SUCCESS CRITERIA
What does success look like? You can glean this from conversations with stakeholders, future state journey mapping
RISKS, SIGNALS & ISSUES/MITIGATIONS
Uncover potential risks, signals and issues through conversations with your stakeholders and project team
A RISK is something that has not yet happened but will possibly occur.
A SIGNAL is something you can notice happening now.
An ISSUE is an event that has already taken place.
A MITIGATION is what we’ll do to avoid the risk, act when there’s a signal or deal with an issue.
SOLUTION/APPROACH (HOW)
A brief description of what the business or department is doing to address the problem. This forms the rationale for the project team.
Template/Prompts included in handouts
OBJECTIVES & KEY RESULTS (OKRs)
Brief overview of the OKRs
Refer back to this when you explain your change activity and how it’s aligned to support these OKRs
Template

## Slide 8: AI-infused Change Canvas
Prompt:
I'm looking to fill in a one-slide Change Canvas with sections: Problem/Opportunity, Solution/Approach, Change Strategies, Success Criteria, Value Proposition, Objectives & Key Results, Key Messages/WIIFM, Risks, Signals & Issues/ Mitigations. You are a change strategist and expert coach, so you will ask me questions about the change for each of these sections, one-by-one, and I will describe the changes, context, plans and outcomes I'm already planning. Include any questions about the change that you need to help complete the section. At the end of the questions of all these sections, report back each section in a few bullets or sentences about the plan. I will use this with my change sponsors, so they know (on one page) what they can expect about this change for their group.
Prompt

## Slide 9
PROBLEM/OPPORTUNITY (WHAT)
There is no consistent or reliable way to capture and share notes from client-facing interactions, leading to missed decisions, misalignment with contracts and financial and relationship risk. Client-facing teams are most impacted, with downstream effects on delivery, internal teams and client satisfaction. This is both a problem to fix and an opportunity to unlock value through AI-enabled efficiency and insights.
VALUE PROPOSITION (WHY)
Employees gain more engaged conversations and lower contractual risk. Leaders gain visibility and insights. The organization strengthens AI maturity, improves client interactions and protects financial and reputational value. The core value is removing administrative work so teams can focus on relationships and outcomes.
AI-Infused Change Canvas
Product Owner: Allie Hartman | Audience: All AgileOne employees | Date: 01/19/26
Change Initiative: Standardized & Automated Notetaking | Change Lead: Allie Hartman | Go Live Date: 03/31/26
CHANGE STRATEGIES (HOW)
Adoption is driven through leadership reinforcement, a sponsor enablement kit, roadshows, targeted communications, AMAs and team-level requirements sessions. Training, demos, user guides and peer success stories support behavior change. Leaders model usage, reinforce expectations and share wins to build momentum.
KEY MESSAGES/WIIFM
This change helps you capture notes automatically so you can focus on strategic, value-added work. It is lightweight, requires only a few new behaviors and delivers multiplied insight in return. Leaders will model and reinforce usage. This is not a performance monitoring tool, and it is not optional.
SUCCESS CRITERIA
Short-term success is visible behavior change, growing usage and real stories of value. Medium-term success includes higher-quality meetings, stronger engagement, improved client satisfaction and reduced risk. Leadership success is measured by efficiency gains, no missed deliverables and elimination of revenue loss tied to missed commitments. Progress is tracked and reported by the AI Project Manager.
RISKS, SIGNALS & ISSUES/MITIGATIONS
Risks include capacity constraints, inconsistent usage and loss of trust in automation. Mitigations include scaling capacity, leadership accountability, reinforcement through communications and transparency around feedback. Human review remains a core safeguard.
SOLUTION/APPROACH (HOW)
Implement an AI-enabled, standardized note-taking solution that automatically converts meeting transcripts into structured, shared notes. Teams review and finalize notes, retaining full control. The solution removes administrative burden, improves consistency and enables better follow-up, preparation and insight generation. Rollout is phased following a successful pilot, allowing for learning and adjustment.
OBJECTIVES & KEY RESULTS (OKRs)
Enable better client conversations and reduce administrative burden while increasing insight generation and AI literacy. Key results include self-reported time savings, improved interaction quality, increasing usage and visible application of insights. All employees onboarded by March 31, with OKRs visible to teams and leadership.
Example

## Slide 10: Micro-Experiments Powered by AI

## Slide 11: Micro-Experiment Examples
Draft two versions of a key change message.
Use AI to assess tone, clarity and likely stakeholder questions before sending.
List key change assumptions.
Ask AI to challenge them and identify where evidence is weak or missing.
Ask AI to summarize themes from recent surveys, emails, chats or feedback.
Look for early signals of confusion, resistance or readiness.
Start with a draft FAQ generated by AI.
Update it weekly based on real questions and AI-identified gaps.
Use AI to generate 3–5 quick pulse questions.
Analyze responses for confidence gaps before finalizing training.
Ask AI to ideate on how to address gaps.
Collect early usage data or anecdotes.
Use AI to cluster friction points and suggest different targeted interventions.
Pilot a new meeting structure for one team or sprint.
Use AI to synthesize notes and surface patterns in engagement or decision quality.
Capture a key decision and its tradeoffs.
Use AI to summarize the rationale so others can understand the “why.”
Assumption Stress Test
FAQ Evolution Test
Adoption Friction Check
Decision Rationale Snapshot
Message Clarity Test
Stakeholder Signal Scan
Training Readiness Pulse
Meeting Format Experiment
Micro-experiment principle: Test one thing. Learn quickly. Adjust visibly.

## Slide 12: The Lab is Open – Stay Curious!
Reimagining the Future of Change Together.
Powered by Curiosity.💡
Allie Hartman
  allie@changecuriositylab.com
  @AlexandraHartman
  @ChangeCuriosityLab
  changecuriositylab.substack.com/
  changecuriositylab.com